## Mtg 2
Issue: | Safety Committee: Meeting 3 of 2016 | Meeting Date: | April 12,2016
Facilitator: | Wade Clouthier
Note Taker | Wade Clouthier
Location | Karson Boardroom at 3232 Carp Road at 9:00 am
Attendees
Present: Wade Clouthier, Kurtis Beveridge, Nicky Iannucci, Ty Arslan, Chris Brent, Neil Falls, Chris Keeping, Andre Burnet,Michelle Richer,
Absent: Troy MacDonald, Ryan wall, David Swan
Previous Meeting Topics Meeting Date : March 9, 2016 |  | Responsibility | Target Date
1 Committee Overview - The Safety Committee is set for next year and will search for new members. - Ty Arlson will be the 2016 HSC Chairman, and will go until the next NCHCA AGM - Committee should prioritize communication needs next year to get better know in the industry - Committee will stay away from commenting on any on going MOL investigation processes to aviod negative media attention |  | Safety Cmmtt | Done
2 Safety Committee Positions - Michelle has taken the safety award nomination tasks - Need someone to do the Newsletter submission Tasks - The Website notices would include examples for the members to use such as tailgate or toolbox talks - All HSC members can bring topics for any of these activities to the Cmtt for review and input - Keep moving ahead on getting more info to crew levels |  | HSC members All | On Going On Going
3 New Whimis Rules - Ty did article for the nNewsletter on it. - Member companies are aware of the new rules through various media avenues. |  |  | Done
4 Lifting Shackles - The information on lifting shackles and frequency of inspections should be brought as a Newsletter article for the spring start up period. - Maybe it could be a lesson learned submission that can become a tool box talk for the members. |  | Safety Cmmtt | On going
Meeting Topics (April 12, 2016) |  | Responsibility | Target Date
1. Monthly Safety Award Submissions Selection - the HSC did not recieve any nomination submissions for February due to slow period for construction activities, and there was discussion on how to increase the numbers - Sewer contractors might have to be pushed for submissions in the winter and road contractors pushed for summer submissions - the HSC decided that the monthly award winners must come from the monthly nominations and if there is no subissions then there will be no monthly award winner. |  | All | 2016
2. Annual NCHCA Award - The new NCHCA Annual Award looks great and thanks to Kurtis efforts it is ready for the AGM. - Could change the name of the award this year for next years AGM presentation, Workers Hurt at Work day celebrations? - The HSC discussed the selection criteria for the annual award, and debated wether saving a life action was greater than doing safety welll all year and maybe saving many lives. It is hard to say how daily activities save how many injuries. HSC will have to define the criteria more for future award selections. - This year's monthly safety award winners were narrowed down to the three best of Karson's Mr Thomas, Coco's Pregenant Lady Assistance, and CCC's Energetic Foreman Promoting Safety with Technology. - The winner by HSC vote was Karson's submission, and Wade wil put notes together for the AGM presentation. |  | All | On going
3. New Issues (a) Recent announcement from MOL allow First Responders to have PST to be covered by WSIB coverage for that industry. Our members should keep it in mind if they have crew members that have witnessed a tragic event, like a traffic accident. (b) COR requirements are needed in Toronto now, and being applied at Federal airports too. Members should look at getting certified soon as it is a lengthy process. (c) ISO Certification can be obtained even if you have issues but pass. There is major and minor issues in their program. This certification is also a slow process to obtain. (d) A good video to watch to see the impact to family members that have lost a loved one to a work accident is "Before Days End by Gerber". It is part of the Threads of Life charity walk theme. Some companies are participating in the local walk, and Bray has taken a lead on it. (e) Discussions have started at the provincial level to have new rules that certian sized projects have a dedicated H&S person on the site fulltime. Quebec has these rules now and define the person's tasks are inclusively H&S. It would level the field on bids on bigger jobs as all bidders would include it. |  |  | On Going
5. Other No other topics were presented so meeting adurned.
Next Meeting | Wednesday May 11, 2016 at 9:00 am at Bray Construction office at Unit 106, 2280 St laurent Blvd
These minutes were recorded by Wade Clouthier and any errors or omissions should be brought to his attention.
Editors note | Alt Enter to edit cell text